## SigNoz POC
Phase | Task ID | Task Name | Description | Owner | Start (Day) | End (Day) | Duration (Days) | Dependencies | Status
Phase 1 - Environmental Setup | 1.2.1 | Provision SigNoz environment | Set up SigNoz (SaaS or self-hosted), capture URL and credentials. | Cyprian | 1 | 2 | 2 | 1.1.5
Phase 1 - Environmental Setup | 1.2.3 | Grant team access | Provide SigNoz access for Dev, QA & SRE Team | Cyprian | 2 | 2 | 1 | 1.2.2
Phase 1 - Environmental Setup | 1.2.2 | Signoz Installation on Ubuntu | Signoz Installation on Ubuntu | SRE | 2 | 2 | 1 | 1.2.1
Phase 1 - Environmental Setup | 1.2.4 | Verify network connectivity | Ensure app services can reach SigNoz endpoint (firewall, TLS). | SRE | 2 | 2 | 1 | 1.2.1
Phase 2 - Telemetry Strategy for Existing App | 2.1.1 | Check and Implement changes with Zero Code Changes | Here we are creating zero code change stratergy for Signoz. In second part we will involve developer and make changes in code to achieve 100% observalibility. | SRE | 2 | 2 | 1 | 1.1.4
Phase 2 - Telemetry Strategy for Existing App | 2.1.2 | Identify best instrumentation points | Choose where to start & end traces and where to record success/failure. | SRE | 2 | 2 | 1 | 2.1.1
Phase 2 - Telemetry Strategy for Existing App | 2.1.3 | Define transaction status model | Define allowed statuses: success, failure; map existing error codes to failure_reason. | SRE | 2 | 2 | 1 | 2.1.2
Phase 2 - Telemetry Strategy for Existing App | 2.1.4 | Define attributes/tags for spans & metrics | Required tags: transaction_id, user_id, amount, currency, channel, env, service, endpoint, failure_reason. | SRE | 2 | 2 | 1 | 2.1.3
Phase 2 - Telemetry Strategy for Existing App | 2.1.5 | Decide sampling & retention | Decide if full tracing for transactions or sampled, considering volume. | SRE | 2 | 2 | 1 | 2.1.4
Phase 3 - Instrumentation & Data Ingestion | 3.3.5 | Fix instrumentation issues | Resolve missing tags, wrong values, or broken traces. | SRE | 6 | 6 | 1 | 3.3.4
Phase 4 - Metric & Query Definition | 4.1.1 | Define queries for transaction totals | Create SigNoz queries for total, successful, and failed transactions over time. | SRE | 6 | 7 | 2 | 3.3.3
Phase 4 - Metric & Query Definition | 4.1.2 | Define query for failure breakdown | Create a query to group failed transactions by failure_reason and count per reason. | SRE | 7 | 7 | 1 | 4.1.1
Phase 4 - Metric & Query Definition | 4.1.3 | Define query for top failure reason | Create a query to find the most common failure_reason for a selected time window. | SRE | 7 | 7 | 1 | 4.1.2
Phase 4 - Metric & Query Definition | 4.1.4 | Define filters for environment & channel | Add filters for env, region, channel (web/mobile), payment_method, etc. | SRE | 7 | 7 | 1 | 4.1.1
Phase 4 - Metric & Query Definition | 4.1.5 | Validate metrics against source-of-truth | Compare metrics in SigNoz vs DB logs or payment provider reports for a sample period. | SRE | 7 | 7 | 1 | 4.1.3
Phase 5 - Dashboard & Failure Traceability | 5.1.1 | Create 'Transaction Overview' dashboard | New SigNoz dashboard for transaction metrics and failures. | SRE | 8 | 8 | 1 | 4.1.3
Phase 5 - Dashboard & Failure Traceability | 5.1.2 | Add total/success/failure panels | Panels showing total transactions, successful, and failed over time. | SRE | 8 | 8 | 1 | 5.1.1
Phase 5 - Dashboard & Failure Traceability | 5.1.3 | Add success rate panel | Derived panel: success_rate = success_total / total * 100, over time. | SRE | 8 | 8 | 1 | 5.1.2
Phase 5 - Dashboard & Failure Traceability | 5.1.4 | Add failure reason breakdown panel | Bar chart or table of failure counts grouped by failure_reason. | SRE | 8 | 9 | 2 | 5.1.3
Phase 5 - Dashboard & Failure Traceability | 5.1.5 | Add top failure reason quick view | Panel showing top 3 failure reasons in the selected time range. | SRE | 9 | 9 | 1 | 5.1.4
Phase 5 - Dashboard & Failure Traceability | 5.1.6 | Add panel to link traces from failures | Panel or link that allows filtering traces by status=failure and failure_reason. | SRE | 9 | 9 | 1 | 5.1.4
Phase 5 - Dashboard & Failure Traceability | 5.1.7 | Add service/endpoint failure distribution | Panel showing which services/endpoints are associated with failures. | SRE | 9 | 9 | 1 | 5.1.6
Phase 5 - Dashboard & Failure Traceability | 5.1.8 | Configure filters and presets | Filters for env, service_name, failure_reason, payment_method, region; default time range (last 24h/7d). | SRE | 9 | 9 | 1 | 5.1.7
Phase 5 - Dashboard & Failure Traceability | 5.1.9 | Review dashboard with product/engineering | Validate that dashboard answers 'how many', 'how many failed', 'why', and 'where'. | SRE | 9 | 9 | 1 | 5.1.8
Phase 6 - Alerting & Run-book | 6.1.1 | Define alert scenarios | Decide when to alert: surge in failures, drop in overall success rate, sudden new failure_reason. | SRE | 9 | 9 | 1 | 5.1.9
Phase 6 - Alerting & Run-book | 6.1.2 | Choose alert thresholds | Example: failure_rate > 5% for 15 min; or failures for a specific reason exceed N per 10 min. | SRE | 9 | 9 | 1 | 6.1.1
Phase 6 - Alerting & Run-book | 6.1.3 | Select notification channels | Choose Slack/email/PagerDuty for transaction failure alerts. | SRE | 9 | 9 | 1 | 6.1.2
Phase 6 - Alerting & Run-book | 6.2.1 | Configure failure rate alerts | Create SigNoz alert(s) for high failure rate or low success rate. | SRE | 10 | 10 | 1 | 6.1.3
Phase 6 - Alerting & Run-book | 6.2.2 | Configure frequent failure_reason alerts | Optional alerts when a specific failure_reason spikes (e.g., gateway_timeout). | SRE | 10 | 10 | 1 | 6.2.1
Phase 6 - Alerting & Run-book | 6.2.3 | Integrate alerts with channels | Connect alerts to Slack/email/incident tool. | SRE | 10 | 10 | 1 | 6.2.2
Phase 6 - Alerting & Run-book | 6.2.4 | Test alerts with controlled failures | Induce or simulate known failure types in test/prod (where safe) to trigger alerts. | SRE | 10 | 10 | 1 | 6.2.3
Phase 6 - Alerting & Run-book | 6.3.1 | Write incident run-book | Document steps: use dashboard to see totals, filter failures by reason, open traces, identify failing service, check logs/deploys. | SRE | 10 | 10 | 1 | 6.2.4
Phase 6 - Alerting & Run-book | 6.3.2 | Define escalation path | Define who gets paged, who analyzes, and who communicates with business. | SRE | 10 | 10 | 1 | 6.3.1
Phase 6 - Alerting & Run-book | 6.3.3 | Publish run-book | Store run-book in wiki/Notion; share with on-call team. | SRE | 10 | 10 | 1 | 6.3.2
Phase 7 - Validation & Scenario Testing | 7.1.1 | Prepare realistic failure scenarios | List likely issues: gateway outage, DB latency, misconfigurations, external API failure. | SRE | 10 | 10 | 1 | 5.1.9
Phase 8 - Stakeholder Demo & Closure | 8.1.6 | Document lessons & backlog | Summarize what worked, issues found, and backlog for further monitoring improvements. | SRE | 13 | 14 | 2 | 8.1.5
Phase 8 - Stakeholder Demo & Closure | 8.1.7 | Finalize POC report | Create a brief report with screenshots, example alerts, and recommendations. | SRE | 14 | 14 | 1 | 8.1.6

## Zero Code Changes Stratergy
Zero-Code Changes Strategy: Instrumentation via Windows Server
Perfect! This is actually the best approach for non-invasive observability. Let me show you how to set this up entirely on your Windows Server without touching your application code.
Architecture: Server-Level Instrumentation
Code
┌─────────────────────────────────────┐
│ Your Existing . NET Application │
│ (ZERO changes to code) │
│ │
│ - Controllers │
│ - Services │
│ - Database calls │
│ - Business logic │
│ (All runs UNCHANGED) │
└────────────────┬────────────────────┘
│
┌────────────┼────────────┐
│ │ │
▼ ▼ ▼
┌────────┐ ┌────────┐ ┌─────────────┐
│ Traces │ │ Logs │ │ Metrics │
│(HTTP, │ │ (IIS) │ │ (Windows │
│ DB) │ │ │ │ Perf Mon) │
└────┬───┘ └───┬────┘ └──────┬──────┘
│ │ │
└──────────┼──────────────┘
│
┌───────────▼───────────┐
│ ETW (Event Tracing │
│ for Windows) │
│ - IIS Logs │
│ - CLR Events │
│ - Performance Counters│
└───────────┬───────────┘
│
┌───────────▼───────────┐
│ OpenTelemetry │
│ Collector │
│ (Windows Service) │
└───────────┬───────────┘
│
┌───────────▼───────────┐
│ OTLP gRPC (4317) │
└───────────┬───────────┘
│
┌───────────▼───────────┐
│ SigNoz / OTel Backend │
│ - ClickHouse Storage │
│ - Dashboard UI │
└───────────────────────┘
Step 1: Install OpenTelemetry Collector (Windows Service)
Download & Extract:
PowerShell
# Run as Administrator
cd C:\
mkdir otel-collector
cd otel-collector
# Download latest version
# Go to: https://github.com/open-telemetry/opentelemetry-collector-releases/releases
# Download: otelcontribcol_windows_amd64.exe
# Or use PowerShell:
Invoke-WebRequest -Uri "https://github.com/open-telemetry/opentelemetry-collector-releases/releases/download/v0.97.0/otelcontribcol_windows_amd64. exe" -OutFile "otelcontribcol. exe"
Step 2: Create Configuration File (No App Changes! )
Create C:\otel-collector\config. yaml:
config.yaml
# OpenTelemetry Collector Configuration
# This is the ONLY file you need to edit!
receivers:
# Receive traces from IIS/ASP.NET
otlp:
Step 3: Install as Windows Service
PowerShell
# Run as Administrator
cd C:\otel-collector
# Create Windows Service
.\otelcontribcol.exe install-service `
-config=config.yaml `
--service-name="OpenTelemetryCollector" `
--service-display-name="OpenTelemetry Collector"
# Start the service
Start-Service -Name "OpenTelemetryCollector"
# Verify it's running
Get-Service -Name "OpenTelemetryCollector"
# Check logs
Get-EventLog -LogName Application -Source "OpenTelemetryCollector" -Newest 20
Step 4: Enable IIS Request Tracing (Optional but Recommended)
PowerShell
# Run as Administrator
# Enable IIS logging
Import-Module WebAdministration
# Enable logging for all sites
Get-ChildItem IIS:\Sites ¦ ForEach-Object {
$_. LogFile. Directory = "C:\inetpub\logs\LogFiles"
$_.LogFile.Format = "W3C"
$_.LogFile. LogExtFileFlags = "Date, Time, ClientIP, UserName, SiteName, ComputerName, ServerIP, Method, UriStem, UriQuery, HttpStatus, Win32Status, BytesSent, BytesRecv, TimeTaken, ServerPort, UserAgent, Referer, Protocol"
}
Step 5: Enable CLR Events for Detailed . NET Tracing
PowerShell
# Run as Administrator
# Enable ETW provider for .NET CLR
logman create trace "dotnet-trace" `
-p ". NET Runtime" 0x0 `
-ow -o "C:\otel-collector\dotnet-trace.etl"
logman start "dotnet-trace"
# This will automatically collect:
# - GC events
# - JIT compilation events
# - Exception events
# - Contention events
Step 6: Configure IIS to Send Traces (OPTIONAL - For Advanced Setup)
If you want IIS to actively send OTLP traces, edit your web.config BUT ONLY if needed:
XML
<!-- This is optional - only if you want IIS-level tracing -->
<!-- Otherwise, ETW collection above handles it -->
<configuration>
<system.webServer>
<httpModules>
<!-- Your existing modules stay here unchanged -->
</httpModules>
</system.webServer>
</configuration>
Actually, you DON'T even need to modify web.config! ETW collection works without it.
Step 7: Set Up SigNoz Backend (Docker on Same Server)
Create C:\otel-collector\docker-compose.yml:
docker-compose.yml
version: '3.8'
services:
clickhouse:
image: clickhouse/clickhouse-server:latest
environment:
Or use Windows Subsystem for Linux (WSL2):
PowerShell
# Install Docker Desktop on Windows
# Then run docker-compose from WSL terminal
Step 8: Verify Everything is Working
PowerShell
# Check if Collector is running
Get-Service -Name "OpenTelemetryCollector" ¦ Select-Object Status
# Check if ports are listening
netstat -ano ¦ findstr "4317\¦4318\¦3301"
# Test connectivity to OTel Collector
Test-NetConnection -ComputerName localhost -Port 4317
# Check Windows Event Viewer for logs
eventvwr.msc
# Navigate to: Application and Services Logs > OpenTelemetry Collector
Step 9: Access SigNoz Dashboard
Open browser and go to:
Code
http://localhost:3301
You should see:
✅ Traces from your . NET application
✅ Metrics from Windows Performance Monitor
✅ Logs from IIS and ETW events
Summary: What Gets Collected (NO CODE CHANGES)
Data Type | Source | How It's Captured
HTTP Traces | IIS Logs | ETW + File Log Receiver
Database Traces | ETW Events | . NET CLR Events
Exceptions | Event Viewer | Windows Event Log Receiver
CPU/Memory | Performance Monitor | Windows PerfCounters Receiver
.NET Metrics | CLR Counters | Windows PerfCounters Receiver
IIS Logs | %SystemRoot%\System32\LogFiles | File Log Receiver
Checklist
Code
✅ Step 1: Download OpenTelemetry Collector
✅ Step 2: Create config. yaml file
✅ Step 3: Install as Windows Service
✅ Step 4: Enable IIS logging
✅ Step 5: Enable ETW for CLR
✅ Step 6: Set up SigNoz backend (Docker/WSL)
✅ Step 7: Verify ports are listening
✅ Step 8: Access SigNoz UI at http://localhost:3301
✅ Your .NET application code = ZERO changes! 🎉
Troubleshooting
PowerShell
# If Collector service won't start
Get-EventLog -LogName Application -Source "OpenTelemetryCollector" -Newest 50
# If ports not responding
netstat -ano ¦ findstr "4317"
# Restart the service
Restart-Service -Name "OpenTelemetryCollector"
# Check if config is valid
.\otelcontribcol.exe validate --config=config.yaml
**This approach is production-ready and requires ZERO modifications to your existing . NET application! Everything happens at the Windows infrastructure level. ** 🚀
Would you like me to help with any specific configuration or troubleshooting?

## Signoz Installation
# Install Docker
sudo yum update -y
sudo yum install -y docker
sudo systemctl start docker
sudo systemctl enable docker
sudo usermod -aG docker ec2-user
# Install Docker Compose
sudo curl -L "https://github.com/docker/compose/releases/latest/download/docker-compose-$(uname -s)-$(uname -m)" -o /usr/local/bin/docker-compose
sudo chmod +x /usr/local/bin/docker-compose
# Clone and start SigNoz
git clone -b main https://github.com/SigNoz/signoz.git
cd signoz/deploy
docker-compose -f docker/clickhouse-setup/docker-compose.yaml up -d
# For 500k transactions, recommended retention:
traces: 15 days
metrics: 30 days
logs: 7 days

## Application Instrumentation
Required NuGet Packages:
<PackageReference Include="OpenTelemetry" Version="1.7.0" />
<PackageReference Include="OpenTelemetry.Exporter.OpenTelemetryProtocol" Version="1.7.0" />
<PackageReference Include="OpenTelemetry.Extensions.Hosting" Version="1.7.0" />
<PackageReference Include="OpenTelemetry.Instrumentation.AspNetCore" Version="1.7.0" />
<PackageReference Include="OpenTelemetry.Instrumentation.Http" Version="1.7.0" />
<PackageReference Include="OpenTelemetry.Instrumentation.SqlClient" Version="1.7.0-beta.1" />
Program.cs Configuration
builder.Services.AddOpenTelemetry()
.ConfigureResource(resource => resource
.AddService("PaymentGateway"))
.WithTracing(tracing => tracing
.AddAspNetCoreInstrumentation()
.AddHttpClientInstrumentation()
.AddSqlClientInstrumentation()
.AddOtlpExporter(opts =>
{
opts.Endpoint = new Uri("http://signoz-ec2:4317");
}))
.WithMetrics(metrics => metrics
.AddAspNetCoreInstrumentation()
.AddHttpClientInstrumentation()
.AddOtlpExporter(opts =>
{
opts.Endpoint = new Uri("http://signoz-ec2:4317");
}));
Custom Payment Instrumentation:
public static class PaymentInstrumentation
{
public static readonly ActivitySource ActivitySource =
new("PaymentGateway.Payments", "1.0.0");
}
// Usage in PaymentService
public async Task<PaymentResult> ProcessPayment(PaymentRequest request)
{
using var activity = PaymentInstrumentation.ActivitySource
.StartActivity("ProcessPayment", ActivityKind.Internal);
activity?.SetTag("payment.amount", request.Amount);
activity?.SetTag("payment.currency", request.Currency);
activity?.SetTag("payment.method", "stripe");
activity?.SetTag("customer.id", request.CustomerId);
try
{
var result = await _stripeService.ChargeAsync(request);
activity?.SetTag("payment.status", result.Status);
activity?.SetTag("payment.transaction_id", result.TransactionId);
return result;
}
catch (Exception ex)
{
activity?.SetStatus(ActivityStatusCode.Error, ex.Message);
activity?.RecordException(ex);
throw;
}
}
Tagging
activity?.SetTag("stripe.payment_intent_id", paymentIntent.Id);
activity?.SetTag("stripe.charge_id", charge.Id);
activity?.SetTag("stripe.customer_id", customerId);
activity?.SetTag("stripe.payment_method_type", paymentMethod.Type);
activity?.SetTag("stripe.status", charge.Status);
activity?.SetTag("stripe.failure_code", charge.FailureCode);
activity?.SetTag("stripe.failure_message", charge.FailureMessage);
SQL Client Configuration:
.AddSqlClientInstrumentation(options =>
{
options.SetDbStatementForText = true;
options.SetDbStatementForStoredProcedure = true;
options.RecordException = true;
options.EnableConnectionLevelAttributes = true;
options.Filter = (command) =>
{
// Exclude health checks
return !command.CommandText.Contains("SELECT 1");
};
})

## Signoz Instance setup
EC2 Instance Sizing for 500k Transactions:
SigNoz All-in-One Instance:
- Instance Type: t3.xlarge (4 vCPU, 16 GB RAM) minimum
- Storage: 500 GB gp3 SSD (for ClickHouse data)
- Network: Enhanced networking enabled
Operating System: Ubuntu
Security Groups:
Inbound Rules:
- Port 3301 (SigNoz UI) - Your IP/VPN
- Port 4317 (OTLP gRPC) - Application subnet
- Port 4318 (OTLP HTTP) - Application subnet
- Port 8080 (Query Service) - Internal
- Port 9000 (ClickHouse HTTP) - Internal