## SigNoz POC
Phase | Task ID | Task Name | Description | Owner | Start (Day) | End (Day) | Duration (Days) | Dependencies | Status
Phase 1 - POC Alignment & Setup | 1.1.1 | Clarify monitoring POC objective | Objective: Use SigNoz to monitor transactions end-to-end and surface counts, failures, reasons, and failing components. | PO/Architect | 1 | 1 | 1
Phase 1 - POC Alignment & Setup | 1.1.2 | Define transaction scope | Agree what a 'transaction' means (e.g., payment, order checkout, booking). | PO/Eng Lead | 1 | 1 | 1 | 1.1.1
Phase 1 - POC Alignment & Setup | 1.1.3 | Document success criteria | Criteria: metrics & traces available in SigNoz, dashboard & alerts configured, ability to drill into failure root cause. | PO | 1 | 1 | 1 | 1.1.2
Phase 1 - POC Alignment & Setup | 1.1.4 | Identify transaction flow services | List backend services, APIs, and external dependencies involved in the transaction flow. | Eng Lead | 1 | 1 | 1 | 1.1.2
Phase 1 - POC Alignment & Setup | 1.1.5 | Identify data points for metrics & traces | Confirm required fields: status, failure_reason, service, endpoint, user/order IDs, etc. | Eng Lead | 1 | 1 | 1 | 1.1.4
Phase 1 - POC Alignment & Setup | 1.2.1 | Provision SigNoz environment | Set up SigNoz (SaaS or self-hosted), capture URL and credentials. | DevOps | 1 | 2 | 2 | 1.1.5
Phase 1 - POC Alignment & Setup | 1.2.2 | Create SigNoz project/tenant | Create project for this monitoring POC. | DevOps | 2 | 2 | 1 | 1.2.1
Phase 1 - POC Alignment & Setup | 1.2.3 | Grant team access | Provide SigNoz access for engineers, SRE, and product owner. | DevOps | 2 | 2 | 1 | 1.2.2
Phase 1 - POC Alignment & Setup | 1.2.4 | Verify network connectivity | Ensure app services can reach SigNoz endpoint (firewall, TLS). | DevOps | 2 | 2 | 1 | 1.2.1
Phase 2 - Telemetry Strategy for Existing App | 2.1.1 | Review existing transaction handling | Inspect current code for where transactions are initiated, processed, and completed. | Engineer | 2 | 2 | 1 | 1.1.4
Phase 2 - Telemetry Strategy for Existing App | 2.1.2 | Identify best instrumentation points | Choose where to start & end traces and where to record success/failure. | Eng Lead | 2 | 2 | 1 | 2.1.1
Phase 2 - Telemetry Strategy for Existing App | 2.1.3 | Define transaction status model | Define allowed statuses: success, failure; map existing error codes to failure_reason. | Eng Lead | 2 | 2 | 1 | 2.1.2
Phase 2 - Telemetry Strategy for Existing App | 2.1.4 | Define attributes/tags for spans & metrics | Required tags: transaction_id, user_id, amount, currency, channel, env, service, endpoint, failure_reason. | Engineer | 2 | 2 | 1 | 2.1.3
Phase 2 - Telemetry Strategy for Existing App | 2.1.5 | Decide sampling & retention | Decide if full tracing for transactions or sampled, considering volume. | Eng Lead | 2 | 2 | 1 | 2.1.4
Phase 3 - Instrumentation & Data Ingestion | 3.1.1 | Integrate OpenTelemetry in core transaction service | Add OTel/SigNoz SDK to primary transaction/payment service. | Engineer | 3 | 4 | 2 | 2.1.4
Phase 3 - Instrumentation & Data Ingestion | 3.1.2 | Configure exporter to SigNoz | Set exporter endpoint, API keys, and env tags (env=dev/stage/prod). | Engineer | 3 | 4 | 2 | 3.1.1
Phase 3 - Instrumentation & Data Ingestion | 3.1.3 | Start a trace at transaction entry point | Create a root span for each transaction (e.g., API endpoint or queue consumer). | Engineer | 4 | 4 | 1 | 3.1.2
Phase 3 - Instrumentation & Data Ingestion | 3.1.4 | Propagate trace context across services | Instrument internal service-to-service calls to keep a single end-to-end trace. | Engineer | 4 | 5 | 2 | 3.1.3
Phase 3 - Instrumentation & Data Ingestion | 3.1.5 | Add spans for external dependencies | Add spans for DB calls, cache, payment gateway API calls, etc. | Engineer | 4 | 5 | 2 | 3.1.4
Phase 3 - Instrumentation & Data Ingestion | 3.2.1 | Instrument transaction metrics - total | Emit metric counter 'transactions_total' for every transaction attempt. | Engineer | 5 | 5 | 1 | 3.1.3
Phase 3 - Instrumentation & Data Ingestion | 3.2.2 | Instrument transaction metrics - success | Emit metric counter 'transactions_success_total' when a transaction completes successfully. | Engineer | 5 | 5 | 1 | 3.2.1
Phase 3 - Instrumentation & Data Ingestion | 3.2.3 | Instrument transaction metrics - failure | Emit metric counter 'transactions_failure_total' with 'failure_reason' tag when a transaction fails. | Engineer | 5 | 5 | 1 | 3.2.1
Phase 3 - Instrumentation & Data Ingestion | 3.2.4 | Tag spans with status & failure_reason | On trace spans, set status=success/failure and add failure_reason where applicable. | Engineer | 5 | 5 | 1 | 3.1.5
Phase 3 - Instrumentation & Data Ingestion | 3.2.5 | Tag spans with service/endpoint | Ensure spans include service_name, endpoint, and any component identifiers. | Engineer | 5 | 5 | 1 | 3.2.4
Phase 3 - Instrumentation & Data Ingestion | 3.3.1 | Deploy instrumentation to staging | Deploy changes to a staging environment. | DevOps | 5 | 5 | 1 | 3.2.5
Phase 3 - Instrumentation & Data Ingestion | 3.3.2 | Trigger sample transactions in staging | Run both successful and failed transactions in staging. | Engineer | 5 | 5 | 1 | 3.3.1
Phase 3 - Instrumentation & Data Ingestion | 3.3.3 | Verify metrics in SigNoz | Check that transactions_total/success_total/failure_total appear with correct counts and tags. | Engineer | 5 | 5 | 1 | 3.3.2
Phase 3 - Instrumentation & Data Ingestion | 3.3.4 | Verify traces in SigNoz | Confirm you can see full traces for transactions and identify where errors occur. | Engineer | 6 | 6 | 1 | 3.3.3
Phase 3 - Instrumentation & Data Ingestion | 3.3.5 | Fix instrumentation issues | Resolve missing tags, wrong values, or broken traces. | Engineer | 6 | 6 | 1 | 3.3.4
Phase 3 - Instrumentation & Data Ingestion | 3.3.6 | Deploy instrumentation to production (controlled) | Roll out to prod with limited risk (e.g., canary or low-traffic period). | DevOps | 6 | 6 | 1 | 3.3.5
Phase 4 - Metric & Query Definition | 4.1.1 | Define queries for transaction totals | Create SigNoz queries for total, successful, and failed transactions over time. | Engineer | 6 | 7 | 2 | 3.3.3
Phase 4 - Metric & Query Definition | 4.1.2 | Define query for failure breakdown | Create a query to group failed transactions by failure_reason and count per reason. | Engineer | 7 | 7 | 1 | 4.1.1
Phase 4 - Metric & Query Definition | 4.1.3 | Define query for top failure reason | Create a query to find the most common failure_reason for a selected time window. | Engineer | 7 | 7 | 1 | 4.1.2
Phase 4 - Metric & Query Definition | 4.1.4 | Define filters for environment & channel | Add filters for env, region, channel (web/mobile), payment_method, etc. | Engineer | 7 | 7 | 1 | 4.1.1
Phase 4 - Metric & Query Definition | 4.1.5 | Validate metrics against source-of-truth | Compare metrics in SigNoz vs DB logs or payment provider reports for a sample period. | Engineer | 7 | 7 | 1 | 4.1.3
Phase 4 - Metric & Query Definition | 4.1.6 | Document metric definitions | Document how each metric is computed and which events/fields they rely on. | PO/Engineer | 7 | 7 | 1 | 4.1.5
Phase 5 - Dashboard & Failure Traceability | 5.1.1 | Create 'Transaction Overview' dashboard | New SigNoz dashboard for transaction metrics and failures. | Engineer | 8 | 8 | 1 | 4.1.3
Phase 5 - Dashboard & Failure Traceability | 5.1.2 | Add total/success/failure panels | Panels showing total transactions, successful, and failed over time. | Engineer | 8 | 8 | 1 | 5.1.1
Phase 5 - Dashboard & Failure Traceability | 5.1.3 | Add success rate panel | Derived panel: success_rate = success_total / total * 100, over time. | Engineer | 8 | 8 | 1 | 5.1.2
Phase 5 - Dashboard & Failure Traceability | 5.1.4 | Add failure reason breakdown panel | Bar chart or table of failure counts grouped by failure_reason. | Engineer | 8 | 9 | 2 | 5.1.3
Phase 5 - Dashboard & Failure Traceability | 5.1.5 | Add top failure reason quick view | Panel showing top 3 failure reasons in the selected time range. | Engineer | 9 | 9 | 1 | 5.1.4
Phase 5 - Dashboard & Failure Traceability | 5.1.6 | Add panel to link traces from failures | Panel or link that allows filtering traces by status=failure and failure_reason. | Engineer | 9 | 9 | 1 | 5.1.4
Phase 5 - Dashboard & Failure Traceability | 5.1.7 | Add service/endpoint failure distribution | Panel showing which services/endpoints are associated with failures. | Engineer | 9 | 9 | 1 | 5.1.6
Phase 5 - Dashboard & Failure Traceability | 5.1.8 | Configure filters and presets | Filters for env, service_name, failure_reason, payment_method, region; default time range (last 24h/7d). | Engineer | 9 | 9 | 1 | 5.1.7
Phase 5 - Dashboard & Failure Traceability | 5.1.9 | Review dashboard with product/engineering | Validate that dashboard answers 'how many', 'how many failed', 'why', and 'where'. | PO/Eng Lead | 9 | 9 | 1 | 5.1.8
Phase 6 - Alerting & Run-book | 6.1.1 | Define alert scenarios | Decide when to alert: surge in failures, drop in overall success rate, sudden new failure_reason. | PO/Eng Lead | 9 | 9 | 1 | 5.1.9
Phase 6 - Alerting & Run-book | 6.1.2 | Choose alert thresholds | Example: failure_rate > 5% for 15 min; or failures for a specific reason exceed N per 10 min. | Eng Lead | 9 | 9 | 1 | 6.1.1
Phase 6 - Alerting & Run-book | 6.1.3 | Select notification channels | Choose Slack/email/PagerDuty for transaction failure alerts. | Eng Lead | 9 | 9 | 1 | 6.1.2
Phase 6 - Alerting & Run-book | 6.2.1 | Configure failure rate alerts | Create SigNoz alert(s) for high failure rate or low success rate. | Engineer | 10 | 10 | 1 | 6.1.3
Phase 6 - Alerting & Run-book | 6.2.2 | Configure frequent failure_reason alerts | Optional alerts when a specific failure_reason spikes (e.g., gateway_timeout). | Engineer | 10 | 10 | 1 | 6.2.1
Phase 6 - Alerting & Run-book | 6.2.3 | Integrate alerts with channels | Connect alerts to Slack/email/incident tool. | Engineer | 10 | 10 | 1 | 6.2.2
Phase 6 - Alerting & Run-book | 6.2.4 | Test alerts with controlled failures | Induce or simulate known failure types in test/prod (where safe) to trigger alerts. | Engineer | 10 | 10 | 1 | 6.2.3
Phase 6 - Alerting & Run-book | 6.3.1 | Write incident run-book | Document steps: use dashboard to see totals, filter failures by reason, open traces, identify failing service, check logs/deploys. | SRE/Engineer | 10 | 10 | 1 | 6.2.4
Phase 6 - Alerting & Run-book | 6.3.2 | Define escalation path | Define who gets paged, who analyzes, and who communicates with business. | SRE/Eng Lead | 10 | 10 | 1 | 6.3.1
Phase 6 - Alerting & Run-book | 6.3.3 | Publish run-book | Store run-book in wiki/Notion; share with on-call team. | SRE | 10 | 10 | 1 | 6.3.2
Phase 7 - Validation & Scenario Testing | 7.1.1 | Prepare realistic failure scenarios | List likely issues: gateway outage, DB latency, misconfigurations, external API failure. | Eng Lead | 10 | 10 | 1 | 5.1.9
Phase 7 - Validation & Scenario Testing | 7.1.2 | Execute scenarios in test/stage | Simulate those scenarios in a non-prod environment. | Engineer | 11 | 11 | 1 | 7.1.1
Phase 7 - Validation & Scenario Testing | 7.1.3 | Observe metrics & dashboard behavior | Confirm metrics and panels behave as expected for each scenario. | Engineer | 11 | 11 | 1 | 7.1.2
Phase 7 - Validation & Scenario Testing | 7.1.4 | Check traceability of failures | Ensure you can follow traces and pinpoint which service/endpoint fails. | Engineer | 11 | 11 | 1 | 7.1.3
Phase 7 - Validation & Scenario Testing | 7.1.5 | Validate alert quality | Make sure alerts trigger appropriately and are actionable (not too noisy). | Engineer | 11 | 11 | 1 | 7.1.4
Phase 7 - Validation & Scenario Testing | 7.1.6 | Adjust dashboards/alerts if needed | Tune thresholds, panels, or filters based on observed behavior. | Eng Lead/Engineer | 11 | 11 | 1 | 7.1.5
Phase 8 - Stakeholder Demo & Closure | 8.1.1 | Prepare demo script | Demo flow: show transaction metrics, failure breakdown, top failure reasons, and trace drill-down. | PO/Engineer | 12 | 12 | 1 | 7.1.6
Phase 8 - Stakeholder Demo & Closure | 8.1.2 | Run demo session | Present to product, engineering, and business stakeholders. | PO/Eng Lead | 12 | 12 | 1 | 8.1.1
Phase 8 - Stakeholder Demo & Closure | 8.1.3 | Collect stakeholder feedback | Capture any additional requirements (e.g., segment by region, customer tier). | PO | 12 | 12 | 1 | 8.1.2
Phase 8 - Stakeholder Demo & Closure | 8.1.4 | Assess POC vs success criteria | Check if all previously defined success criteria are met. | PO/Eng Lead | 13 | 13 | 1 | 8.1.3
Phase 8 - Stakeholder Demo & Closure | 8.1.5 | Decide on broader rollout | Decide whether to extend SigNoz to more services/flows. | Leadership/Eng Lead | 13 | 13 | 1 | 8.1.4
Phase 8 - Stakeholder Demo & Closure | 8.1.6 | Document lessons & backlog | Summarize what worked, issues found, and backlog for further monitoring improvements. | PO/Eng Lead | 13 | 14 | 2 | 8.1.5
Phase 8 - Stakeholder Demo & Closure | 8.1.7 | Finalize POC report | Create a brief report with screenshots, example alerts, and recommendations. | PO | 14 | 14 | 1 | 8.1.6